## Development_Stages
Action No	Definition	Comment	Deadline	State
1	Create communication layer with socket (class Communication)	Needs to be tested! Sending and receiving data!	10.10.2021	DONE
2	List comments and categorize them for logical order!	Needs to be cleared for Library	11.10.2021	PROGRESS
3	Implement all decided commands to main py file	Needs to be added for testing comments	11.10.2021	PROGRESS
4	Create shutdown procedure (class Shutdown)	Needs to be done for safe shutdown	12.10.2021	NOT STARTED
5	Create watchdog procedure (class Watchdog) - Thread	Needs to be done for communication lose safety	12.10.2021	NOT STARTED
6	Create datalogger (class Datalogger) - Thread	Needs to be done for operational logging	13.10.2021	NOT STARTED
7	Create ramp up and down for Voltage, Current, Power (class Rampup) - Thread		NA.	NOT STARTED
8	Charging Discharging and Cycling Battery (class Battery) - Thread		NA.	NOT STARTED

## Commands
Command No	Command Name	Description (This command used to)	Category	Protocol	Command Description & Page	Added to Main Library	Tested	Class Name		Query	Space	Terminator	Positive Intergers	Floationg Points	True/False or 1/0	Allowed to use or skip the command
1	*IDN?<term>	Read the identification string of the SM15K	Query	Socket - Send&Receive Data	General Instruction - 8	YES	YES	GeneralInstructions		?	<sp>	<term> \n	<NR1>	<NR2>	<boolean>	[]
2	*PUD?<term>	Read the protected user data	Query	Socket - Send&Receive Data	General Instruction - 8	YES	YES	GeneralInstructions
3	*CLS<term>	Clear the error queue	Command	Socket - Send Data	General Instruction - 8	YES	YES	GeneralInstructions
4	*RST<term>	Set the power supply in a save defined state	Command	Socket - Send Data	General Instruction - 8	YES	YES	GeneralInstructions
5	SOURce:VOLtage:MAXimum?<term>	Read the maximum output voltage	Query	Socket - Send&Receive Data	Source Subsystem - 9	YES	YES	SourceSubsystem
6	SOURce:CURrent:MAXimum?<term>	Read the maximum output current	Query	Socket - Send&Receive Data	Source Subsystem - 9	YES	YES	SourceSubsystem
7	SOURce:CURrent:NEGative:MAXimum?<term>	Read the maximum negative output current	Query	Socket - Send&Receive Data	Source Subsystem - 9	YES	YES	SourceSubsystem
8	SOURce:POWer:MAXimum?<term>	Read the maximum output power	Query	Socket - Send&Receive Data	Source Subsystem - 9	YES	YES	SourceSubsystem
9	SOURce:POWer:NEGative:MAXimum?<term>	Read the maximum negative output power	Query	Socket - Send&Receive Data	Source Subsystem - 9	YES	YES	SourceSubsystem
10	SOURce:VOLTage<sp><NR2><term>	To set the output voltage of the power supply	Command	Socket - Send Data	Source Subsystem - 9	YES	YES	SourceSubsystem
11	SOURce:VOLTage?<term>	To see last voltage set point of the power supply	Query	Socket - Send&Receive Data	Source Subsystem - 9	YES	YES	SourceSubsystem
12	SOURce:CURrent<sp><NR2><term>	To set the output current of the power supply	Command	Socket - Send Data	Source Subsystem - 9	YES	YES	SourceSubsystem
13	SOURce:CURrent?<term>	To see last current set point of the power supply	Query	Socket - Send&Receive Data	Source Subsystem - 9	YES	YES	SourceSubsystem
14	SOURce:CURrent:NEGative<sp><NR2><term>	To set the output negative current of the power supply	Command	Socket - Send Data	Source Subsystem - 9	YES	YES	SourceSubsystem
15	SOURce:CURrent:NEGative?<term>	To see last negative current set point of the power supply	Query	Socket - Send&Receive Data	Source Subsystem - 9	YES	YES	SourceSubsystem
16	SOURce:POWer<sp><NR2><term>	To set the output power of the power supply	Command	Socket - Send Data	Source Subsystem - 10	YES	YES	SourceSubsystem
17	SOURce:POWer?<term>	To see last output power set point of the power supply	Query	Socket - Send&Receive Data	Source Subsystem - 10	YES	YES	SourceSubsystem
18	SOURce:POWer:NEGative<sp><NR2><term>	To set the negative output power of the power supply	Command	Socket - Send Data	Source Subsystem - 10	YES	YES	SourceSubsystem
19	SOURce:POWer:NEGative?<term>	To see last negative output power set point of the power supply	Query	Socket - Send&Receive Data	Source Subsystem - 10	YES	YES	SourceSubsystem
20	SOURce:VOLtage:STEpsize?<term>	To read the programming stepsize of the output voltage	Query	Socket - Send&Receive Data	Source Subsystem - 10	YES	YES	SourceSubsystem
21	SOURce:CURrent:STEpsize?<term>	To read the programming stepsize of the output current	Query	Socket - Send&Receive Data	Source Subsystem - 10	YES	YES	SourceSubsystem
22	SOURce:POWer:STEpsize?<term>	To read the programming stepsize of the output power	Query	Socket - Send&Receive Data	Source Subsystem - 10	YES	YES	SourceSubsystem
23	MEASure:VOLtage?<term>	To measure output voltage of the power supply	Query	Socket - Send&Receive Data	Measure Subsystem - 10	YES	YES	MeasureSubsystem
24	MEASure:CURrent?<term>	To measure output current of the power supply	Query	Socket - Send&Receive Data	Measure Subsystem - 10	YES	YES	MeasureSubsystem
25	MEASure:POWer?<term>	To measure output power of the power supply	Query	Socket - Send&Receive Data	Measure Subsystem - 10	YES	YES	MeasureSubsystem
26	MEASure:INStrument<sp>AH,STATE,<setting><term>	To enable the current measurement instrument <setting>: OFF, ON, SUSPEND or RESUME Turning the instrument ON will reset all previous measurements	Command	Socket - Send Data	Measure Subsystem - 11	YES	YES	MeasureSubsystem
27	MEASure:INStrument<sp>AH,STATE?<term>	To read enable status (OFF, ON, SUSPEND or RESUME)	Query	Socket - Send&Receive Data	Measure Subsystem - 11	YES	YES	MeasureSubsystem
28	MEASure:INStrument<sp>AH,TIMEHR?<term>	To read the time the instrument is active (hours with three decimals) / If the instrument is not enabled, the result will be zero	Query	Socket - Send&Receive Data	Measure Subsystem - 11	YES	YES	MeasureSubsystem
29	MEASure:INStrument<sp>AH,TIMESEC?<term>	To read the time the instrument is active (seconds with one decimal) / If the instrument is not enabled, the result will be zero	Query	Socket - Send&Receive Data	Measure Subsystem - 11	YES	YES	MeasureSubsystem
30	MEASure:INStrument<sp>AH,POS,TOTAL?<term>	To read the total Ah for positive current - w Scientifiec Notation / If the instrument is not enabled, the result will be zero.	Query	Socket - Send&Receive Data	Measure Subsystem - 11	YES	YES	MeasureSubsystem
31	MEASure:INStrument<sp>AH,NEG,TOTAL?<term>	To read the total Ah for negative current - w Scientifiec Notation / If the instrument is not enabled, the result will be zero.	Query	Socket - Send&Receive Data	Measure Subsystem - 11	YES	YES	MeasureSubsystem
32	MEASure:INStrument<sp>AH,POS,IMIN?<term>	To read minimum positive current during the time the instrument is enabled. / Result will be in Ampere, if the instrument is not enabled, the result will be zero.	Query	Socket - Send&Receive Data	Measure Subsystem - 11	YES	YES	MeasureSubsystem
33	MEASure:INStrument<sp>AH,POS,IMAX?<term>	To read maximum positive current during the time the instrument is enabled. / Result will be in Ampere, if the instrument is not enabled, the result will be zero.	Query	Socket - Send&Receive Data	Measure Subsystem - 11	YES	YES	MeasureSubsystem
34	MEASure:INStrument<sp>AH,NEG,IMIN?<term>	To read minimum negative current during the time the instrument is enabled. / Result will be in Ampere, if the instrument is not enabled, the result will be zero.	Query	Socket - Send&Receive Data	Measure Subsystem - 11	YES	YES	MeasureSubsystem
35	MEASure:INStrument<sp>AH,NEG,IMAX?<term>	To read maximum negative current during the time the instrument is enabled. / Result will be in Ampere, if the instrument is not enabled, the result will be zero.	Query	Socket - Send&Receive Data	Measure Subsystem - 11	YES	YES	MeasureSubsystem
36	MEASure:INStrument<sp>WH,STATE,<setting><term>	To enable the power measurement instrument / <setting>: OFF, ON, SUSPEND or RESUME / Turning the instrument ON will reset all previous measurements	Command	Socket - Send Data	Measure Subsystem - 11	YES	YES	MeasureSubsystem
37	MEASure:INStrument<sp>WH,STATE?<term>	To read enable status (OFF, ON, SUSPEND or RESUME)	Query	Socket - Send&Receive Data	Measure Subsystem - 11	YES	YES	MeasureSubsystem
38	MEASure:INStrument<sp>WH,TIMEHR?<term>	To read the time the instrument is active (hours with three decimals) / If the instrument is not enabled, the result will be zero	Query	Socket - Send&Receive Data	Measure Subsystem - 11	YES	YES	MeasureSubsystem
39	MEASure:INStrument<sp>WH,TIMESEC?<term>	To read the time the instrument is active (seconds with one decimal) / If the instrument is not enabled, the result will be zero	Query	Socket - Send&Receive Data	Measure Subsystem - 11	YES	YES	MeasureSubsystem
40	MEASure:INStrument<sp>WH,POS,TOTAL?<term>	To read the total Wh for positive current - w Scientifiec Notation / If the instrument is not enabled, the result will be zero.	Query	Socket - Send&Receive Data	Measure Subsystem - 11	YES	YES	MeasureSubsystem
41	MEASure:INStrument<sp>WH,NEG,TOTAL?<term>	To read the total Wh for negative current - w Scientifiec Notation / If the instrument is not enabled, the result will be zero.	Query	Socket - Send&Receive Data	Measure Subsystem - 12	YES	YES	MeasureSubsystem
42	MEASure:INStrument<sp>WH,POS,PMIN?<term>	To read minimum positive power during the time the instrument is enabled. / Result will be in Watts, if the instrument is not enabled, the result will be zero.	Query	Socket - Send&Receive Data	Measure Subsystem - 12	YES	YES	MeasureSubsystem
43	MEASure:INStrument<sp>WH,POS,PMAX?<term>	To read maximum positive power during the time the instrument is enabled. / Result will be in Watts, if the instrument is not enabled, the result will be zero.	Query	Socket - Send&Receive Data	Measure Subsystem - 12	YES	YES	MeasureSubsystem
44	MEASure:INStrument<sp>WH,NEG,PMIN?<term>	To read minimum negative power during the time the instrument is enabled. / Result will be in Watts, if the instrument is not enabled, the result will be zero.	Query	Socket - Send&Receive Data	Measure Subsystem - 12	YES	YES	MeasureSubsystem
45	MEASure:INStrument<sp>WH:NEG,PMAX?<term>	To read maximum negative power during the time the instrument is enabled. / Result will be in Watts, if the instrument is not enabled, the result will be zero.	Query	Socket - Send&Receive Data	Measure Subsystem - 12	YES	YES	MeasureSubsystem
46	MEASure:TEMperature?<term>	To read highest internal temperature of the power supply	Query	Socket - Send&Receive Data	Measure Subsystem - 12	YES	YES	MeasureSubsystem
47	SYSTem:RSD[:STAtus]<sp><boolean><term>	To activate and deactivate remote shutdown Boolean = 0, 1, OFF (Unlocked), ON (Locked)	Command	Socket - Send Data	System Subsystem - 13	YES	YES	SystemSubsystem
48	SYSTem:RSD[:STAtus]?<term>	To read last RSD settings	Query	Socket - Send&Receive Data	System Subsystem - 13	YES	YES	SystemSubsystem
49	SYSTem:LIMits:VOLtage<sp><NR2>,<boolean><term>	To set the limits of the voltage / Off = disabled, On = enabled	Command	Socket - Send Data	System Subsystem - 13	YES	YES	SystemSubsystem
50	SYSTem:LIMits:VOLtage?	To read last voltage limit setting	Query	Socket - Send&Receive Data	System Subsystem - 13	YES	YES	SystemSubsystem
51	SYSTem:LIMits:CURrent<sp><NR2>,<boolean><term>	To set the limits of the positive current / Off = disabled, On = enabled	Command	Socket - Send Data	System Subsystem - 13	YES	YES	SystemSubsystem
52	SYSTem:LIMits:CURrent?	To read last positive current limit setting	Query	Socket - Send&Receive Data	System Subsystem - 14	YES	YES	SystemSubsystem
53	SYSTem:LIMits:CURrent:NEGative<sp><NR2>,<boolean><term>	To set the limits of the negative current / Off = disabled, On = enabled	Command	Socket - Send Data	System Subsystem - 14	YES	YES	SystemSubsystem
54	SYSTem:LIMits:CURrent:NEGative?	To read last negative current limit setting	Query	Socket - Send&Receive Data	System Subsystem - 14	YES	YES	SystemSubsystem
55	SYSTem:LIMits:POWer<sp><NR2>,<boolean><term>	To set the limits of the positive power / Off = disabled, On = enabled	Command	Socket - Send Data	System Subsystem - 14	YES	YES	SystemSubsystem
56	SYSTem:LIMits:POWer?	To read last positive power limit setting	Query	Socket - Send&Receive Data	System Subsystem - 14	YES	YES	SystemSubsystem
57	SYSTem:LIMits:POWer:NEGative<sp><NR2>,<boolean><term>	To set the limits of the negative power / Off = disabled, On = enabled	Command	Socket - Send Data	System Subsystem - 14	YES	YES	SystemSubsystem
58	SYSTem:LIMits:POWer:NEGative?	To read last negative power limit setting	Query	Socket - Send&Receive Data	System Subsystem - 14	YES	YES	SystemSubsystem
59	SYSTem:FROntpanel:HIGhlight	To highlight front panel / - Display on front will blink for about 2 seconds / - Buzzer on front is on for about 2 seconds.	Command	Socket - Send Data	System Subsystem - 14	YES	YES	SystemSubsystem
60	SYSTem:FROntpanel[:STAtus]<sp><boolean><term>	To lock the front panel / Boolean = 0, 1, OFF (Unlocked), ON (Locked)	Command	Socket - Send Data	System Subsystem - 14	YES	YES	SystemSubsystem
61	SYSTem:FROntpanel[:STAtus]?<term>	To read the last settings about the front lock	Query	Socket - Send&Receive Data	System Subsystem - 14	YES	YES	SystemSubsystem
62	SYSTem:FROntpanel:CONtrols<sp><boolean><term>	To lock or unluck front panel and/or control / Boolean = 0 (Menu), 1 (Menu & Controls), OFF (Menu), ON (Menu & Controls)	Command	Socket - Send Data	System Subsystem - 14	YES	YES	SystemSubsystem
63	SYSTem:FROntpanel:CONtrols?	To read the last settings about the front lock&control	Query	Socket - Send&Receive Data	System Subsystem - 14	YES	YES	SystemSubsystem
	SYSTem:TIMe<sp><hour>,<minute>,<second><term>	To set time as hour, minute, second / Hour = 0-23 - Minute = 0-59 - Second = 0-59	Command	Socket - Send&Receive Data	System Subsystem - 15	YES	NO	SystemSubsystem
	SYSTem:TIMe?<term>	To read the current time, answer <hour>:<minute>:<second> / The answer will be “UNKNOWN” in case the time was not set.	Query	Socket - Send&Receive Data	System Subsystem - 15	YES	NO	SystemSubsystem
	SYSTem:DATe<sp><year>,<month>,<day><term>	To set the date as year, month, day / Year = 2019-2099 - Month = 1-12 - Day = 1-31	Command	Socket - Send&Receive Data	System Subsystem - 15	YES	NO	SystemSubsystem
	SYSTem:DATe?<term>	To read the current date, answer <year>-<month>-<day> / The answer will be “UNKNOWN” in case the time was not set.	Query	Socket - Send&Receive Data	System Subsystem - 15	YES	NO	SystemSubsystem
	SYSTem:ERRor?<term>	To read the error message, The SM15K returns the first error and clears it from the queue / If there are no errors (so the queue is empty), the result of this query will be : 0,None<term> / So after 10 readings of SYSTem:ERRor? the queue is empty for sure, or after using the *CLS command.	Query	Socket - Send&Receive Data	System Subsystem - 15	YES	NO	SystemSubsystem
	SYSTem:WARning?<term>	To read the warning message, If there are no warnings, the result of this query will be: 0,None<term>	Query	Socket - Send&Receive Data	System Subsystem - 15	YES	NO	SystemSubsystem
	SYSTem:COMmunicate:WATchdog<sp>SET,<NR1><term>	To set the Watchdog timer (in ms) - <NR1>= 20…10000	Command	Socket - Send&Receive Data	System Subsystem - 16	YES	NO	SystemSubsystem
	SYSTem:COMmunicate:WATchdog<sp>SET?<term>	To read the last setting: (valid until Timeout)	Query	Socket - Send&Receive Data	System Subsystem - 16	YES	NO	SystemSubsystem
	SYSTem:COMmunicate:WATchdog?<term>	To read the current state of the Watchdog timer with three possibilities; / 20…10000<term> Current timer value in ms / 0<term> Timeout. Clears indicator on Front panel and Web / -1<term> Clears Timeout, Watchdog is off / Note: The timer will be set to 2.5ms and expires very quickly. The indicator on the Front panel and Web will be activated. Enable, disable or query the state of the Watchdog timer to clear the indicators.	Query	Socket - Send&Receive Data	System Subsystem - 16	YES	NO	SystemSubsystem
	SYSTem:COMmunicate:WATchdog<sp>STOP<term>	To disable the Watchdog timer	Command	Socket - Send&Receive Data	System Subsystem - 16	YES	NO	SystemSubsystem
	SYSTem:COMmunicate:WATchdog<sp>TEST<term>	To test the Watchdog timer	Command	Socket - Send&Receive Data	System Subsystem - 16	YES	NO	SystemSubsystem
	OUTPut<sp><boolean><term>	To switch power supply on/off - boolean = 0, 1, OFF, ON	Command	Socket - Send&Receive Data	Output Subsystem - 17	NO	NO	OutputSubsystem
	OUTPut?<term>	To read the last stage of the output	Query	Socket - Send&Receive Data	Output Subsystem - 17	MO	NO	OutputSubsystem